## Gantt Chart Example
Gantt Chart Example from "Meeting the Writer's Deadline"
Tasks | Days allocated for each task
| Days 1-5 | Days 6-11 | Days 12 - 17 | Days 18 - 23 | Days 24-29 | Days 30-35 | Days 36-41 | Days 42-47 | Days 48-53 | Continues
Idea dev. | 5 days
Research |  | 5 days
Writing
Ch. 1 |  |  | 2 days
Ch. 2 |  |  | 3 days
Ch. 3 |  |  |  | 2 days
Ch. 4 |  |  |  | 3 days
Ch.r 5 |  |  |  |  | 2 days
Ch. 6 |  |  |  |  | 2 days
Ch. 7 |  |  |  |  | 1 day | 1 day
Ch. 8 | [5 empty] | 2 days
Resources | [5 empty] | 2 days
Bio, etc. | [6 empty] | 3 days
Edits | [7 empty] | 5 days
Proofread | [8 empty] | 5 days
NOTE: This list continues for the length of the project through production